## PM
Gerência de projetos
Objetivo | Descrição | Capacidade de controle sobre o trabalho | Controle de qualidade | Comunicação com o cliente | Manutenção e rastreabilidade entre artefatos | Criação e manutenção do Projeto de software | Metodologia de desenvolvimento | Gerência de modificações | Gerência de erros | Gerência sobre o projeto como um todo | Integração da equipe | Gerência de riscos | Capacidade de previsão de entrega
PM.01 | The Project Plan for the execution of the project is developed according to the Statement of Work and reviewed and accepted by the Customer. The Tasks and Resources necessary to complete the work are sized and estimated. | 4 | 3 | 5 | 0 | 2 | 5 | 0 | 0 | 5 | 4 | 4 | 0
PM.O2 | Progress of the project is monitored against the Project Plan and recorded in the Progress Status Record. Corrections to remediate problems and deviations from the plan are taken when project targets are not achieved. Closure of the project is performed to get the Customer acceptance documented in the Acceptance Record. | 3 | 5 | 5 | 2 | 0 | 1 | 0 | 0 | 5 | 3 | 3 | 0
PM.03 | The Change Requests are addressed through their reception and analysis. Changes to software requirements are evaluated for cost, schedule and technical impact. | 3 | 5 | 4 | 4 | 0 | 5 | 5 | 0 | 2 | 0 | 0 | 5
PM.04 | Review meetings with the Work Team and the Customer are held. Agreements are registered and tracked. | 4 | 4 | 5 | 3 | 0 | 1 | 5 | 0 | 5 | 5 | 0 | 5
PM.05 | Risks are identified as they develop and during the conduct of the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 5 | 0
PM.06 | A software Version Control Strategy is developed. Items of Software Configuration are identified, defined and baselined. Modifications and releases of the items are controlled and made available to the Customer and Work Team. The storage, handling and delivery of the items are controlled. | 4 | 0 | 5 | 5 | 0 | 3 | 0 | 0 | 4 | 4 | 0 | 5
PM.07 | Software Quality Assurance is performed to provide assurance that work products and processes comply with the Project Plan and Requirements Specification. | 4 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 3 | 0 | 0 | 3
Atividade | Descrição | PM.01 | PM.02 | PM.03 | PM.04 | PM.05 | PM.06 | PM.07
PM.1 | Project Planning | x |  |  |  | x | x | x
PM.2 | Project Plan Execution |  | x | x | x | x |  | x
PM.3 | Project Assessment and Control |  | x
PM.4 | Project Closure |  | x
Note on D1: The purpose of the Project Management process is to establish and carry out in a systematic way the Tasks of the software implementation project, which allows complying with the project’s Objectivesin the expected quality, time and costs. This part of ISO/IEC 29110 is intended to be used by the VSE to establish processes to implement any development approach or methodology including, e.g., agile, evolutionary, incremental, test driven development, etc. based on the VSE organization or project needs.
Note on B13: The Project Planning activity documents the planning details needed to manage the project. The activity provides: - Reviewed Statement of Work and the Tasks needed to provide the contract Deliverables and to satisfy Customer requirements. - Project lifecycle, including task dependencies and duration. - Project quality assurance strategy through verification and validation of work products/Deliverables, Customer and Work Team reviews. - Work Team and Customer roles and responsibilities. - Project Resources and training needs. - Estimates of effort, cost and schedule. - Identified project risks. - Project version control and baseline strategy. - Project Repository to store, handle and deliver controlled product and document versions and baselines.
Note on B14: The Project Plan Execution activity implements the documented plan on the project. The activity provides: - Progress Status Record of the project updated. - Analyzed and evaluated change requests to the plan impacting cost, schedule and technical requirements. - Approved changes to the plan. - Reviews and agreements with the Work Team (WT) and Customer (CUS). - Back up of the Project Repository, and its recovery if necessary.
Note on B15: The Project Assessment and Control activity evaluates the performance of the plan against documented commitments. The activity provides: - Evaluation of actual plan performance and progress against targets. - Identified and evaluated significant cost, schedule and technical performance deviations and problems. - Review of project risks and identification of new risks. - Documented change requests, appropriate corrective action defined, and changes tracked to closure.
Note on B16: The Project Closure activity provides the project’s documentation and products in accordance with contract requirements. The activity provides: - Delivery of the product as specified in the Delivery Instructions. - Support of Customer product acceptance in accordance to Delivery Instructions. - Completion of the project and sign of the Acceptance Record.

## SI
Implementação de Software
Nível de impacto
Objetivo | Descrição | Capacidade de controle sobre o trabalho | Controle de qualidade | Comunicação com o cliente | Manutenção e rastreabilidade entre artefatos | Criação e manutenção do Projeto de software | Metodologia de desenvolvimento | Gerência de modificações | Gerência de erros | Gerência sobre o projeto como um todo | Integração da equipe | Gerência de riscos | Capacidade de previsão de entrega
SI.01 | Tasks of the activities are performed through the accomplishment of the current Project Plan. | 5 | 4 | 2 | 0 | 4 | 4 | 0 | 0 | 5 | 0 | 0 | 5
SI.02 | Software requirements are defined, analyzed for correctness and testability, approved by the Customer, baselined and communicated. | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 | 3 | 3 | 5
SI.03 | Software architectural and detailed design is developed and baselined. It describes the Software Components and internal and external interfaces of them. Consistency and traceability to software requirements are established. | 4 | 5 | 0 | 5 | 5 | 5 | 0 | 0 | 2 | 0 | 0 | 3
SI.04 | Software Components defined by the design are produced. Unit test are defined and performed to verify the consistency with requirements and the design. Traceability to the requirements and design are established. | 5 | 5 | 0 | 5 | 5 | 5 | 0 | 0 | 2 | 0 | 0 | 2
SI.05 | Software is produced performing integration of Software Components and verified using Test Cases and Test Procedures. Results are recorded at the Test Report. Defects are corrected and consistency and traceability to Software Design are established. | 5 | 5 | 0 | 5 | 3 | 5 | 0 | 0 | 2 | 0 | 0 | 3
SI.06 | A Software Configuration, that meets the Requirements Specification as agreed to with the Customer, which includes user, operation and maintenance documentations is integrated, baselined and stored at the Project Repository. Needs for changes to the Software Configuration are detected and related change requests are initiated. | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 3 | 0 | 3
SI.07 | Verification and Validation Tasks of all required work products are performed using the defined criteria to achieve consistency among output and input products in each activity. Defects are identified, and corrected; records are stored in the Verification/Validation Results. | 5 | 5 | 0 | 3 | 0 | 5 | 4 | 5 | 3 | 0 | 0 | 3
Atividade | Descrição | SI.01 | SI.02 | SI.03 | SI.04 | SI.05 | SI.06 | SI.07
SI.1 | Software Implementation Initiation | x
SI.2 | Software Requirements Analysis |  | x |  |  |  | x | x
SI.3 | Software Architectural and Detailed Design |  |  | x |  |  | x | x
SI.4 | Software Construction |  |  |  | x |  | x | x
SI.5 | Software Integration and Tests |  |  |  |  | x | x | x
SI.6 | Product Delivery | [5 empty] | x | x
Note on D1: The purpose of the Software Implementation process is the systematic performance of the analysis, design, construction, integration and tests activities for new or modified software products according to the specified requirements. This part of ISO/IEC 29110 is intended to be used by the VSE to establish processes to implement any development approach or methodology including, e.g., agile, evolutionary, incremental, test driven development, etc. based on the VSE organization or project needs.
Note on B13: The Software Implementation Initiation activity ensures that the Project Plan established in Project Planning activity is committed to by the Work Team. The activity provides: - Review of the Project Plan by the Work Team to determine task assignment. - Commitment to Project Plan by the Work Team and Project Manager. - An implementation environment established.
Note on B14: The Software Requirements Analysis activity analyzes the agreed Customer’s requirements and establishes the validated project requirements. The activity provides: - Work Team review of the Project Plan to determine task assignment. - Elicitation, analysis and specification of Customer’s requirements. - Agreement on the Customer requirements. - Verification and validation of requirements. - Version control of the software requirements products.
Note on B15: The Software Architectural and Detailed Design activity transforms the software requirements to the system software architecture and software detailed design. The activity provides: - Work Team review of the Project Plan to determine task assignment. - Design software architecture, Software Components and associated interfaces. - Detailed design of the Software Components and interfaces. - Work Team review of the Requirements Specification. - Software Design verified and defects corrected. - VerifiedTest Cases and Test Procedures for integration testing. - Traceability of the software requirements to the Software Design, Test Cases and Test Procedures. - Design products and documents under version control. NOTE Software Architecture and Detailed Design can be performed separately according to the project schedule.
Note on B16: The Software Construction activity develops the software code and data from the Software Design. The activity provides: - Work Team review of the Project Plan to determine task assignment. - Work Team review of the Software Design to determine software construction sequence. - Coded Software Components and applied unit tests. - Traceability between Software Components and Software Design.
Note on B17: The Software Integration and Tests activity ensures that the integrated Software Components satisfy the software requirements. The activity provides: - Work Team review of the Project Plan to determine task assignment. - Understanding of Test Cases and Procedures and the integration environment. - Integrated Software Components, corrected defects and documented results. - Traceability of requirements and design to the integrated software product. - Documented and verified operational and software user documentations. - Verified Software baseline.
Note on B18: The Product Delivery activity provides the integrated software product to the Customer. The activity provides: - Work Team review of the Project Plan to determine task assignment. - Verified Maintenance Documentation. - Delivery of the software product and applicable documentation in accordance with the Delivery Instructions.

## Plan1
Classificação das estratégias pela empresa
Gerência de erros | 1
Gerência sobre o projeto como um todo | 3
Integração da equipe | 4
Gerência de riscos | 2
Capacidade de previsão de entrega | 5
Comunicação com o cliente | 6
Exemplo (simplificado) de pergunta e dos pesos das respostas
Você avisa seu cliente quando uma nova versão está disponível?
Sempre | ( ) | 1
A maioria das vezes | ( ) | 2
Algumas vezes | ( ) | 3
Raramente | (x) | 4
Nunca | ( ) | 5
Peso da pergunta p/cada estratégia x peso da resposta x classificação da estratégia pela empresa = classificação por estratégia
Gerência de erros |  | 1 | x | 4 | x | 1 | = | 4
Gerência sobre o projeto como um todo |  | 2 | x | 4 | x | 3 | = | 24
Integração da equipe |  | 0 | x | 4 | x | 4 | = | 0
Gerência de riscos |  | 1 | x | 4 | x | 2 | = | 8
Capacidade de previsão de entrega |  | 4 | x | 4 | x | 5 | = | 80
Comunicação com o cliente |  | 5 | x | 4 | x | 6 | = | 120